## Chart
Note: | Update your remaining effort in E column.
to use: | update effort applied for each day and everything else will auto populate
Sprint Burndown
source ===> https://youtu.be/J17dOgmjS2c?feature=shared
|  |  | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thu | Fri
Developer | Progress | Initial Estimate | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Aiden | Effort Applied | N/A | 2 | 1 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 1
| Remaining Effort | 18 | 16 | 15 | 13 | 11 | 8 | 6 | 5 | 3 | 1 | 0
| Ideal Trend | 18 | 16.2 | 14.4 | 12.6 | 10.8 | 9 | 7.2 | 5.4 | 3.6 | 1.8 | 0
An | Effort Applied | N/A | 0 | 1 | 3 | 1 | 2 | 4 | 1 | 4 | 1 | 2
| Remaining Effort | 19 | 19 | 18 | 15 | 14 | 12 | 8 | 7 | 3 | 2 | 0
| Ideal Trend | 19 | 17.1 | 15.2 | 13.3 | 11.4 | 9.5 | 7.6 | 5.7 | 3.8 | 1.9 | 0
Kameron | Effort Applied | N/A | 0 | 2 | 2 | 3 | 3 | 2 | 3 | 2 | 3 | 3
| Remaining Effort | 23 | 23 | 21 | 19 | 16 | 13 | 11 | 8 | 6 | 3 | 0
| Ideal Trend | 23 | 20.7 | 18.4 | 16.1 | 13.8 | 11.5 | 9.2 | 6.9 | 4.6 | 2.3 | 0
Jacob | Effort Applied | N/A | 0 | 1.5 | 2 | 2 | 2 | 4.5 | 1.5 | 3 | 2 | 1
| Remaining Effort | 22 | 22 | 20.5 | 18.5 | 16.5 | 14.5 | 10 | 8.5 | 5.5 | 3.5 | 2.5
| Ideal Trend | 22 | 19.8 | 17.6 | 15.4 | 13.2 | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0
Parth | Effort Applied | N/A | 0 | 2 | 3 | 1 | 2 | 3 | 2 | 3 | 1 | 2
| Remaining Effort | 19 | 19 | 17 | 14 | 13 | 11 | 8 | 6 | 3 | 2 | 0
| Ideal Trend | 19 | 17.1 | 15.2 | 13.3 | 11.4 | 9.5 | 7.6 | 5.7 | 3.8 | 1.9 | 0
Khoung | Effort Applied | N/A | 0 | 1 | 3 | 1 | 2 | 4 | 2 | 3 | 1 | 2
| Remaining Effort | 19 | 19 | 18 | 15 | 14 | 12 | 8 | 6 | 3 | 2 | 0
| Ideal Trend | 19 | 17.1 | 15.2 | 13.3 | 11.4 | 9.5 | 7.6 | 5.7 | 3.8 | 1.9 | 0
Team | Effort Applied | N/A | 2 | 8.5 | 15 | 10 | 14 | 19.5 | 10.5 | 17 | 10 | 11
| Remaining Effort | 120 | 118 | 109.5 | 94.5 | 84.5 | 70.5 | 51 | 40.5 | 23.5 | 13.5 | 2.5
| Ideal Trend | 120 | 108 | 96 | 84 | 72 | 60 | 48 | 36 | 24 | 12 | 0