## BackLog
Backlog:
Work Items in priority order | Complexity Level 1 - 5 so we can give work based on experience | Effort Points 1 - 1 hours ratio | Due Date Internal - for dev External - for client | Due Date External
Milestone 2 – Network Diagram | 4 | 20 | 2023-12-10 | 2023-12-11
Milestone 2 – Security Library | 4 | 40 | 2023-12-10 | 2023-12-11
Milestone 2 – User Management Library | 4 | 60 | 2023-12-10 | 2023-12-11
BRD Redrafting for approval | 3 | 10 | 2023-12-20 | 2024-01-01
Note: Milestone 2 work item estimates are proportionate to the amount of points each represents.
Developer sign-off: AH KF JP AN KN PT